## Project Charter
Project Genaral Project Information
Project Name:- | MindSprint - Placement Preparation & Skill Learning App
Project Champion:-
Project Sponsor:- | Lok Jagruti Institute of Computer Applications (LJICA)
Project Manager:-
Stackholders:- | Sapoliya Dhruv, Vavaliya Dvarkesh, Prajapati Krunal
Start Date:- | 22/07/2026
Expected Complate Date:-
Project details
Mission | To deliver a unified mobile-first placement preparation and technical skill learning platform with adaptive testing, offline resilience, and automated weak spot detection.
Vision | Empower college students and job seekers across Gujarat to excel in competitive campus placements and technical interviews through gamified, curriculum-aligned mobile learning.
Scope | Development of full-stack mobile application (React Native / Expo), Node.js/Express REST API, MongoDB database, offline static caching, timed mock exams, AI doubt clearing, and course video catalog.
Out Of Scope | Physical classroom lectures, third-party payment gateways, proprietary hardware testing.
Date | 22/07/2026

## Project Road Mape
MindSprint | July 2026 |  |  |  | August 2026 |  |  |  | September 2026 |  |  |  | October 2026
| Sprint 1 |  |  |  | Sprint 2 |  |  |  | Sprint 3 |  |  |  | Sprint 4
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3
Analysis
Design
Coding
Testing
Documentation
MindSprint | Sprint 1 Week 1: July 2026; Sprint 2 Week 1: August 2026; Sprint 3 Week 1: September 2026; Sprint 4 Week 1: October 2026 |  | November 2026
| Sprint 1 Week 1: Sprint 1; Sprint 1 Week 4: Sprint 2; Sprint 2 Week 3: Sprint 3; Sprint 3 Week 2: Sprint 4; Sprint 4 Week 1: Sprint 5 | Sprint 6
| Week1 | Week2 | Week3 | Week1 | Week2 | Week3 | Week1 | Week2 | Week3 | Week1 | Week2 | Week3 | week1 | Week2 | Week3 | Week1 | Week2 | Week3
Analysis
Design
Coding
Testing
Documentation

## Project Plan
Project Manager
Project Deliverable |  | Yes
Scope Statement |  | MindSprint - Placement Preparation & Skill Learning App
Start Date |  | 22/07/2026
End Date
| Task Name |  | Responsible Name | Start Date | End Date | Day | Status
| Sprint 1 |  | Dhruv | 22/07/2026 | 08/08/2026 | 15 | Complete
| Sprint Planning & Stack Architecture |  | Dhruv | 22/07/2026 | 26/07/2026 | 5 | Complete
| Login & Registration Backend (JWT) |  | Dvarkesh | 27/07/2026 | 31/07/2026 | 5 | Complete
| Authentication UI & Navigation Routing |  | Krunal | 01/08/2026 | 08/08/2026 | 5 | Complete
| Sprint 2 |  | Dhruv | 10/08/2026 | 28/08/2026 | 15 | Complete
| Syllabus Selector & User Profile Module |  | Dhruv | 10/08/2026 | 14/08/2026 | 5 | Complete
| Course & Video Catalog REST APIs |  | Dhruv,Krunal,Dvarkesh | 17/08/2026 | 21/08/2026 | 5 | Complete
| Course Catalog UI & Chapter Reader |  | Dvarkesh | 24/08/2026 | 28/08/2026 | 5 | Complete
| Sprint 3 |  | Dhruv | 31/08/2026 | 18/09/2026 | 15 | Complete
| Question Bank Backend & Company Tagging |  | Krunal,Dvarkesh | 31/08/2026 | 04/09/2026 | 5 | Complete
| Timed Mock Exam Engine UI & Palette |  | Dhruv,Dvarkesh | 07/09/2026 | 11/09/2026 | 5 | Complete
| In-Exam Scratchpad & Timer Logic |  | Dhruv | 14/09/2026 | 18/09/2026 | 5 | Complete
| Sprint 4 |  | Dhruv | 21/09/2026 | 09/10/2026 | 15 | Complete
| Score Evaluation & Percentage Logic |  | Krunal | 21/09/2026 | 25/09/2026 | 5 | Complete
| Weak Spot Detection & Accuracy Analytics |  | Dhruv,Krunal | 28/09/2026 | 02/10/2026 | 5 | Complete
| Results Summary UI & Category Cards |  | Dvarkesh,Krunal | 05/10/2026 | 09/10/2026 | 5 | Complete
| Sprint 5 |  | Dhruv | 12/10/2026 | 30/10/2026 | 15 | Complete
| AI Doubt Solver Text & Voice Processing |  | Dvarkesh | 12/10/2026 | 16/10/2026 | 5 | Complete
| Camera OCR Text Extraction & Matching |  | Dhruv,Krunal | 19/10/2026 | 23/10/2026 | 5 | Complete
| Swipeable Flashcards & Daily Streak |  | Krunal,Dvarkesh | 26/10/2026 | 30/10/2026 | 5 | Complete
| Sprint 6 |  | Dhruv | 02/11/2026 |  | 15 | In Progress
| Offline Resilience & Local Fallback Layer |  | Krunal | 02/11/2026 | 06/11/2026 | 5 | Complete
| UAT Testing, Bug Fixes & Optimization |  | Dhruv,Dvarkesh | 09/11/2026 | 13/11/2026 | 5 | In Progress
| Final Documentation & Deployment |  | Dhruv,Dvarkesh,Krunal | 16/11/2026 |  | 5 | In Progress

## User Story
| Project Name | MindSprint - Placement Preparation & Skill Learning App
Project Manager
User Story Id | As a <Type of user> | I want to <perform some task> | So that I can<achive some goal> | Priority
1 | Student | Registration & Login | Secure account access & track saving | High
2 | Placement Aspirant | Filter questions by Company (TCS, Infosys, Amazon) | Prepare for targeted campus recruitment tests | High
3 | Student | Timed Mock Exam Engine with Palette | Practice real-time speed & pacing | High
4 | Student | Automated Score & Weak Spot Detection | Identify weak topics for focused revision | High
5 | IT Skill Learner | Video Masterclasses & e-Textbooks | Learn technical concepts & syllabus chapters | High
6 | Student | AI Doubt Solver & Camera OCR | Resolve tricky questions instantly with step-by-step solutions | High
7 | Student | Swipeable Flashcards & Daily Streak | Maintain daily study consistency & quick recall | High
8 | Admin / Faculty | Question Bank & Syllabus Management | Update verified questions and curriculum topics | High

## Release Plan
Sprint | Task | Start Date | End Date | Duration | Status | Release Date
Sprint 1: Architecture, Navigation & Auth (JWT) | Sprint Planing | 2025-12-08 | 2025-12-12 | 5 | Complate | 2025-12-26
| Login & Registration | 2025-12-15 | 2025-12-19 | 5 | Complate | 2025-12-26
| Auth UI | 2025-12-22 | 2025-12-26 | 5 | Complate | 2025-12-26
Sprint 2: Course Catalog & Video Masterclasses | User/Profile Module | 2025-12-29 | 2026-01-02 | 5 | Complate | 2026-01-16
| Product/Category APIs | 2026-01-05 | 2026-01-09 | 5 | Complate | 2026-01-16
| Product Listing UI | 2026-01-12 | 2026-01-16 | 5 | Complate | 2026-01-16
Sprint 3: Timed Mock Exam Engine & Palette | Cart/Rental Backend | 2026-01-19 | 2026-01-23 | 5 | Complate | 2026-02-06
| Cart/Checkout UI | 2026-01-26 | 2026-01-30 | 5 | Complate | 2026-02-06
| Payment Flow + Notifications | 2026-02-02 | 2026-02-06 | 5 | Complate | 2026-02-06
Sprint 4: Weak Spot Detection & Result Evaluation | Admin Backend((Users/Products/Offers) | 2026-02-09 | 2026-02-13 | 5 | Complate | 2026-02-27
| Admin Panel UI | 2026-02-16 | 2026-02-20 | 5 | Complate | 2026-02-27
| Roles/Permissions + Reports | 2026-02-20 | 2026-02-27 | 5 | Complate | 2026-02-27
Sprint 5: AI Doubt Solver (OCR) & Flashcards | Search/Filter + Offer Engine | 2026-03-02 | 2026-03-06 | 5 | Complate | 2026-03-20
| Order History + Invoice | 2026-03-09 | 2026-03-12 | 5 | Complate | 2026-03-20
| Integration Testing + Bug Fixes | 2026-03-16 | 2026-03-20 | 5 | Complate | 2026-04-15
Sprint 6: Offline Resilience, UAT & Deployment | Performance + Security Hardening | 2026-03-23 | 2026-03-27 | 5 | Complate | 2026-04-15
| UAT Fixes + Documentation | 2026-03-30 | 2026-04-03 | 5 | Complate | 2026-04-15
| Deployment | 2026-04-06 | 2026-04-10 | 5 | Complate | 2026-04-15

## Product Backlog
Product Backlog
Task name | Story | Sprint Ready | Priority | Status | Story Point | Assign to sprint | Story Point | Sprint Hours
Sprint Planning & Stack Setup | Yes | Yes | High | Completed | 3 | Dhruv | 1 | 1 To 4
Mobile Navigation & Design System | Yes | Yes | High | Completed | 8 | Dvarkesh | 3 | 4 To 8
User Auth & JWT Session Service | Yes | Yes | High | Completed | 5 | Krunal | 5 | 8 To 16
Database Schemas & Mongoose Models | Yes | Yes | High | Completed | 8 | Dhruv | 8 | 16 To 24
Course Catalog & Video Player Module | Yes | Yes | High | Completed | 13 | Dhruv,Krunal,Dvarkesh | 13 | 24 To 40
Syllabus Selector (GTU / GSEB) | Yes | Yes | High | Completed | 3 | Dvarkesh
Timed Mock Exam Engine & Palette | Yes | Yes | High | Completed | 13 | Dhruv,Krunal,Dvarkesh
Weak Spot Detection Logic | Yes | Yes | High | Completed | 8 | Dhruv,Krunal,Dvarkesh
AI Doubt Solver & Camera OCR | Yes | Yes | High | Completed | 13 | Krunal,Dvarkesh
Offline ApiService Fallback Testing | Yes | Yes | High | Completed | 8 | Dhruv,Krunal,Dvarkesh
Agile & Project Documentation | Yes | Yes | High | Completed | 8 | Dhruv,Krunal,Dvarkesh
Sprint Backlog
Task name | Story | Sprint Ready | Priority | Status | Story Point | Assign to sprint
Sprint 1 | Yes | Yes | High | Complated | 14 | Dhruv
Sprint Planing | Yes | Yes | High | Complated | 3 | Dhruv
Login & Registration | Yes | Yes | High | Complated | 8 | Dvarkesh
Auth UI | Yes | Yes | High | Complated | 3 | Krunal
Sprint 2 | Yes | Yes | High | Complated | 24 | Dhruv
User / Syllabus Selector Module | Yes | Yes | High | Complated | 8 | Dhruv
Course & Video Catalog REST APIs | Yes | Yes | High | Complated | 13 | Dhruv,Krunal,Dvarkesh
Course Catalog UI & Chapter Reader | Yes | Yes | High | Complated | 3 | Dvarkesh
Sprint 3 | Yes | Yes | High | Complated | 26 | Dhruv
Question Bank Backend & Company Tagging | Yes | Yes | High | Complated | 13 | Krunal,Dvarkesh
Timed Mock Exam Engine UI & Palette | Yes | Yes | High | Complated | 5 | Dhruv,Dvarkesh
In-Exam Scratchpad & Timer Logic | Yes | Yes | High | Complated | 8 | Dhruv
Sprint 4 | Yes | Yes | High | Complated | 29 | Dhruv
Score Evaluation & Percentage Logic | Yes | Yes | High | Complated | 13 | Krunal
Weak Spot Detection & Accuracy Analytics | Yes | Yes | High | Complated | 8 | Krunal,Dhruv
Results Summary UI & Category Cards | Yes | Yes | High | Complated | 8 | Krunal,Dvarkesh
Sprint 5 | Yes | Yes | High | Complated | 25 | Dhruv
AI Doubt Solver Text & Voice Processing | Yes | Yes | High | Complated | 8 | Dvarkesh
Camera OCR Text Extraction & Matching | Yes | Yes | High | Complated | 8 | Krunal,Dhruv
Swipeable Flashcards & Daily Streak | Yes | Yes | High | Complated | 8 | Krunal,Dvarkesh
Sprint 6 | No | Yes | Medium | Complated | 15 | Dhruv
Offline Resilience & Local Fallback Layer | No | Yes | Medium | Complated | 5 | Krunal
UAT Testing, Bug Fixes & Optimization | No | Yes | Medium | Complated | 3 | Dhruv,Dvarkesh
Final Project Documentation & Review Prep | No | Yes | Medium | Complated | 7 | Kiran,Dvarkesh

## Test Plan
Project Name | MindSprint - Placement Preparation & Skill Learning App |  | Browser/Device | Android Mobile (Expo Go / APK) & Web Browser
Test Case | 1 |  | Version | Android 14 / Chrome v130 / Brave v1.71
Written By | Dhruv |  | Description | Full Regression & Acceptance Testing
Test By | Krunal, Dvarkesh |  | Test on | Mobile Device (Pixel / Samsung) & Laptop
Test # | Test Date | Action | Expected Result | Actual Result | Pass
1 | 22/07/2026 | Mobile Navigation & Theme Mode | Seamless screen navigation and Dark/Light mode toggle | Flawless theme switching and stack navigation | Pass
2 | 31/07/2026 | Student Registration & Login | Validates email/password constraints & issues JWT token | Login & registration functional with validation errors | Pass
3 | 18/09/2026 | Timed Mock Exam & Palette | Countdown timer runs; palette reflects status & submits | Test executes with live countdown and palette status | Pass
4 | 09/10/2026 | Weak Spot Detection Logic | Score calculated; categories <60% tagged as weak spots | Automated breakdown correctly tags weak categories | Pass
5 | 06/11/2026 | Offline ApiService Fallback | App falls back to static verified JSON on network drop | Zero crash; offline static data returned instantly | Pass

## Burndown chart
Sprint Days | Planned Hours | Actual Hours Remaining | Total Remaining Tasks
1 | 104 | 104 | 13
2 | 96 | 98 | 12
3 | 88 | 90 | 11
4 | 80 | 75 | 10
5 | 72 | 70 | 9
6 | 64 | 65 | 8
7 | 56 | 58 | 7
8 | 48 | 48 | 6
9 | 40 | 43 | 5
10 | 32 | 30 | 4
11 | 24 | 25 | 3
12 | 16 | 15 | 2
13 | 8 | 8 | 1
14 | 0 | 0 | 0